## Analysis (hidden)
UI | Functionality | TestData
1) Company name field difference on ui In preprod Company name field is not present 2) File Type filed difference on ui In preprod File Type provided field is different from that of in UAT 3) Files required to be uploaded are also different for Preprod 4) Inside file, for preprod activation date is not present | For all Clients in File Upload Scenario | 2 files environment specific
Locators- ui elements designing | Overall all scenarios almost 10 % entirely
Drop down value product type Ex IFT and Internal fund transfer Environment specific values
2) ifsc avaialble are diff in both enviornment. 3) delay has been put at some places in preprod. 4) product naming convention is different. 5) package name changed for amsel | single and bulk transactions

## Execution StatusOld (hidden)
Scenario | Environment | Pass | Fail | Remarks | Workaround
AUTOREL - SCN_006_FileUpload_AutoAuthAutoSend | Pre Prod | 4 | 8 |  | 1. Need to discard company name 2. Need to change File Type 3. Need to change File
AUTOAEL - SIngle Transaction | Pre Prod | 58 | 10 | 1) ifsc avaialble are diff in both enviornment. 2) delay has been put at some places in preprod. 3) product naming convention is different. 4) package name changed for amsel
BULK Transaction

## Execution Status
Scenario Desc | Scenario Count | Case/Steps Count | Environment | Pass | Not Executed | Fail | Execution Date | Backlog | Remarks | Fixes done | No of Scenarios fixed
Single data entry | 10 | 410 | Preprod | 400 | 0 | 10 | 2023-06-05 |  | final status not as expected, intermittent click | updated ifsc when it was not able to select
Bulk data entry | 27 | 867 | Preprod | 813 |  | 54 | 2023-06-05 |  | final status not as expected, not able to click, intermittent click | updated ifsc when it was not able to select
File Upload | 6 | 145 | Preprod | 134 |  | 11 | 2023-06-06 |  | final status not as expected, intermittent click | Updated verify status when not able to select
Instrument printing | [6 empty] | 2023-06-06
Single data entry | 191 | 191 | UAT | 186 |  | 5 | 2023-06-06 |  | Test data issue
Bulk data entry | 11 | 788 | UAT | 523 | 174 | 97 | 2023-06-06 |  | Not fetching text at some places due to page load issue, sending account not available in uat .
Bulk data entry | 8 | 550 | UAT | 500 |  | 50 | 2023-06-06 |  | Application click issue, checker not able to approve receiver, element not found.
Single data entry | 10 | 278 | Preprod | 278 | 0 | 0 | 2023-06-07
Bulk data entry | 17 | 1003 | Preprod | 977 | 0 | 26 | 2023-06-07 |  | status - returned for amsel ,click intermittent, not fetched status for sdel,unknown constructor related error(intermittent)
Receiver | 1 | 42 | Preprod | 42 | 0 | 0 | 2023-06-07
File Upload | 14 | 503 | Preprod | 489 |  | 12 | 2023-06-07 |  | status is not updated someimes, checkbox clicks are intermittant | put delyas when required | 1
Single data entry | 10 | 278 | Preprod | 278 | 0 | 0 | 2023-06-09
Bulk data entry | 17 | 1003 | Preprod | 992 | 0 | 11 | 2023-06-09 |  | Transaction status not as expected due to application issue
Receiver | 1 | 42 | Preprod | 42 | 0 | 0 | 2023-06-09
bulk data entry - backlog | 1 | 46 | Preprod | 46 | 0 | 0 | 2023-06-14
SDE & BDE | 9 | 518 | Preprod | 510 | 0 | 8 | 2023-06-16 |  | status not as expected
SDE | 8 | 339 | Preprod | 328 |  | 11 | 2023-06-19 |  | Status no as expected(application issue), unable to find element(script issue). | ran after rerun | 1
BDE | 15 | 1056 | Preprod | 987 |  | 69 | 2023-06-19 |  | Status no as expected(application issue), unable to find element(script issue),not able to approve (script) | put refresh screen | 2
Receiver | 1 | 42 | Preprod | 42 |  |  | 2023-06-19
Reporter | 1 | 24 | Preprod | 24 |  |  | 2023-06-19
SDE & BDE | 3 | 190 | Preprod | 190 |  |  | 2023-06-20 |  |  | chnaged amount ,changed checker crn | 3
BDE | 1 | 84 | Preprod | 84 |  |  | 2023-06-21 |  | there was issue with added receiver which was not populating while doing transaction. | changed packagename for receivers as suggested by sayali | 1
FU | 4 | 190 | Preprod | 190 |  |  | 2023-06-21 |  | Verifying optimzed fucntionality
SDE | 8 | 339 |  | 339 |  | 0 | 2023-06-22
BDE | 15 | 1056 | Preprod | 1046 |  | 10 | 2023-06-22 |  | Status no as expected(application issue), for sce- 9,29,44
Receiver | 1 | 42 | Preprod | 42 |  |  | 2023-06-22
Reports | 1 | 24 | Preprod | 24 |  |  | 2023-06-22
File Upload | 9 | 314 | Preprod | 314 |  | 0 | 2023-06-22
FU | 4 | 408 | Preprod | 408 |  |  | 2023-06-26
Suitewise Execution | 17 Suites | 206 methods | Preprod | 124 Methods | 36 skip | 46 | 2023-06-26 | 82 | Failure reason :Status not as expected, click intermittent(application issue), javascript error(scripting error). Skipped : skipped due to failure of dependant cases.
FU | 11 | 643 | Preprod | 643 |  | 0 | 2023-06-27
SDE | 8 | 339 |  | 339 |  | 0 | 2023-06-28
BDE | 15 | 1056 | Preprod | 1046 |  | 10 | 2023-06-28 |  | Status no as expected(application issue), for sce- 9(BDE_ManualApproveAutoSend),29(BDE_Weekly/General Holiday), 44(BDE_Checker User Unable to Send Transactions)
Receiver | 1 | 42 | Preprod | 42 |  |  | 2023-06-28
Reports | 1 | 24 | Preprod | 24 |  |  | 2023-06-28
FU | 5 | 454 | Preprod | 454 |  |  | 2023-06-28

## Sheet1
Scenario Count | Case/Steps Count | Environment | Pass | Not Executed | Fail | Execution Date | Backlog | Remarks
80 |  | Preprod | 55 | 6 | 25 | 2023-06-26 | 31 | failure reason : unable to find element not executed : instrument printing scenarios | Arslan
Amarja

## Environmental flexibility
Seperated test data file wrt environments
Global properties file updated wrt environment selection
Drop down values Ex IFT | Entered in test data excel file
Performance issues | Handled with wait time
IFSC code difference | Handled via excel file as per environment
File Type filed difference on ui | Entered in test data excel file

## Scenarios Covered
Scenarios | Environment | Comments
Receiver creation through data entry | Both | error in uat for ASHL client
Debit failed scenarios | Both
Rejected scenario for data entry | Both
Send functionality for AVM/SVM | Both
Debit failed batch data entry scenarios | Both
Discard related scenarios | Both
Negative below | Both
Role and User level access | Both
Limit scenario | Both
Duplicate reference number | Both
Backdated scenarios | Both
Intrument printing test cases | Both
Beneficiary upload scenarios | Both
Duplicate redciver creation | Both
User level account access scenario | Both
Client Level Limit check throgh multiple files upload scenarios | Both
Maker Level Limit Check scenarios | Both
Checker Level Limit Check scenarios | Both
File Reject Scenarios | Both
AVM/SVM related scenarios for File | Both
Future dated File Upload Scenarios | Both
Batch Data Entry weekly holiday scenario | Both

## Execution - Pre prod
Automation Testing - Round 1
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 10 | 278 | 278 | 0 | 0 | 2023-06-07 | 0
| Bulk data entry | 17 | 1003 | 977 | 0 | 26 | 2023-06-07 | 26 | 1]Fail :ASHL -Bulk data entry : intermittent javascript error (script issue) 2. AMSEL,Single data entry L- Bulk data entry : status not as expected(application issue)
| Receiver | 1 | 42 | 42 | 0 | 0 | 2023-06-07 | 0
| File Upload | 20 | 648 | 623 | 0 | 23 | 2023-06-07 |  | File status not as expected and intermittent click issue
26
Automation Testing - Round 2
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution
Payments and Retrofits | Single data entry | 10 | 278 | 278 | 0 | 0 | 2023-06-09 | 0
| Bulk data entry | 17 | 1003 | 992 | 0 | 11 | 2023-06-09 | 11 | 1]Fail : AEL,AMSEL,ASHL-Bulk data entry - status not as expected(application issue)
| Receiver | 1 | 42 | 42 | 0 | 0 | 2023-06-09 | 0
| File Upload | 4 | 190 | 190 | 0 | 0 | 2022-06-21 |  | final status not as expected, intermittent click issue
11
Automation Testing - Round 3
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 10 | 325 | 325 |  | 0 | 2023-06-13 | 0
| Bulk data entry | 17 | 1089 | 1031 |  | 58 | 6/13/2023 | 58 | 1]Fail : 7 : AEL Bulk data entry -AVM : javascript error (Script issue) 29- ASHL Bulk data entry weekly ,44-OREL -Bulk data entry Unable to send,35-Single data entry L Bulk data entry - approve All,38-Single data entry L Bulk data entry - Debit Failed---Status not as expected due to application issue.
| Receiver | 1 | 42 | 42 | 0 | 0 | 2023-06-13
| Report | 1 | 24 | 24 | 0 | 0 | 2023-06-13
| File Upload | 4 | 408 | 408 | 0 | 0 | 2023-06-26
58
Automation Testing - Round 4
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 8 | 339 | 328 |  | 11 | 2023-06-19 | 11 | Status no as expected(application issue), unable to find element(script issue).
| Bulk data entry | 15 | 1056 | 987 |  | 69 | 2023-06-19 | 69 | Status no as expected(application issue), unable to find element(script issue),not able to approve (script)
| Receiver | 1 | 42 | 42 |  | 0 | 2023-06-19
| Reporter | 1 | 24 | 24 |  | 0 | 2023-06-19
| File Upload | 11 | 643 | 643 |  | 0 | 2023-06-27
80
Automation Testing - Round 5
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 2 | 100 | 100 |  |  | 2023-06-20 | 0 | Application and script issues
| Bulk data entry | 2 | 174 | 174 |  |  | 2023-06-20 | 0 | there was issue with added receiver which was not populating while doing transaction.
| Receiver | [5 empty] | 2023-06-20
| Reporter | [5 empty] | 2023-06-20
| File Upload | 9 | 314 | 314 | 0 | 0 | 2023-06-22
Automation Testing - Round 6
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 8 | 339 | 339 |  |  | 2023-06-22 | 0
| Bulk data entry | 15 | 1056 | 1046 |  | 10 | 2023-06-22 | 0 | Status no as expected(application issue), for sce- 9(BDE_ManualApproveAutoSend),29(BDE_Weekly/General Holiday), 44(BDE_Checker User Unable to Send Transactions)
| Receiver | 1 | 42 | 42 |  |  | 2023-06-22
| Reporter | 1 | 24 | 24 |  |  | 2023-06-22
| File Upload | 5 | 454 | 454 | 0 | 0 | 2023-06-28
Automation Testing - Round 7
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry | 8 | 339 | 339 |  | 0 | 2023-06-28 | 0
| Bulk data entry | 15 | 1056 | 1046 |  | 10 | 2023-06-28 | 0 | Status no as expected(application issue), for sce- 9(BDE_ManualApproveAutoSend),29(BDE_Weekly/General Holiday), 44(BDE_Checker User Unable to Send Transactions)
| Receiver | 1 | 42 | 42 |  | 0 | 2023-06-28
| Reporter | 1 | 24 | 24 |  | 0 | 2023-06-28
File Upload
Automation Testing - Round 8
Automation Scripts Execution - Chrome Browser
Module | Scenarios | Scenario count | Test Cases (Steps) | Pass | Not Executed | Fail | Execution Date | Backlog of Execution | Remarks
Payments and Retrofits | Single data entry
Bulk data entry
Receiver
Reporter
File Upload